## Backlog
HitRadar — Sprint / Phase Backlog (Retrospective Reconstruction)
Source basis: Git commits, canonical notebooks, reports, validation artifacts, and PR #2. Unknown ownership is intentionally omitted.
Sprint / Phase | Epic | Task | Acceptance Criteria | Status | Evidence Path | Commit / PR Evidence | Notes
Epic 1 · 2026-07 | Data foundation | Audit source dataset and establish schema | Coverage and schema are documented from repository evidence | Complete | 6.TAI_LIEU/6.1.bao_cao/DATASET_AUDIT_REPORT.md | 08bb8c4, 8ab3416 | 586,672 processed rows; observed years 1900–2021.
Epic 1 · 2026-07 | PostgreSQL | Create schemas, raw/clean tables, views and indexes | Canonical SQL and validation reports exist | Partial / DB unavailable | 2.DATABASE_SQL/; 6.TAI_LIEU/6.1.bao_cao/DATABASE_SCHEMA.md | 0f430e1, c0299eb | Repository evidence exists; NB02 was not re-executed in the final hotfix because no local PostgreSQL service was available.
Epic 1 · 2026-07 | Cleaning & quality | Normalize clean layer and run data-quality gates | Cleaning rules and gate results are documented | Complete | 9.SCRIPTS/clean_raw_to_clean.py; 6.TAI_LIEU/6.1.bao_cao/DATA_QUALITY_REPORT.md | cfee95c, 3608633 | No new cleaning computation in final hotfix.
Epic 1 · 2026-07 | EDA | Produce canonical EDA notebooks and findings | Six EDA notebooks and reports are present | Complete | 3.NOTEBOOKS/3.4.eda/; 6.TAI_LIEU/6.1.bao_cao/EDA_FINDINGS.md | 3936a7e, e093c71 | Predictive/descriptive evidence; not causal.
Epic 2 · 2026-07 | Feature engineering | Implement leakage-safe engineered features | 16 candidates evaluated; 14 selected; train-only learned statistics | Complete | 3.NOTEBOOKS/3.5.feature_engineering/05_feature_engineering.ipynb; FINAL_SUBMISSION/evidence/feature_contract.json | 043d803, bcde803 | Shared feature logic is used by training and deployment.
Epic 2 · 2026-07/08 | Temporal modeling | Select winner on <=2017/2018 and evaluate 2019+ once | Winner locked before final test; metrics and model checksums preserved | Complete / preserved | 3.NOTEBOOKS/3.6.modeling/06_machine_learning.ipynb; 4.MODELS/hitradar_popularity/final_test_metrics.json | bcde803, 221ea53 | Notebook 06 preserved; not retrained in final repository hotfix.
Epic 3 · 2026-08 | Deployment | Expose FastAPI and Streamlit interfaces | API/direct parity, health, AppTest and support policy evidence pass | Complete | 5.UNG_DUNG/5.1.backend_api/; 5.UNG_DUNG/5.2.frontend/ | dfff705, eb5f343 | Post-2020 inputs are allowed with warning.
Round 4 · 2026-08-14 | Reproducibility | Package sanitized evidence snapshot | Checksums, manifest, environment and tests are recorded | Complete | FINAL_SUBMISSION/; 5.UNG_DUNG/validation/ | 34eeeb8, 221ea53, PR #2 | Snapshot is not standalone; external local artifacts are required.
Final hotfix · 2026-08-14 | Repository hygiene | Untrack large processed data and sanitize tracked paths | No forbidden runtime artifacts tracked; repository-wide path validator passes | In progress | 9.SCRIPTS/validate_public_repository.py | final-repository-hotfix branch | Legacy Git history may still contain historical artifacts; no history rewrite.
Final hotfix · 2026-08-14 | Coursework deliverables | Restore XLSX/DOCX evidence and remove ambiguity/placeholders | Files are non-zero, readable and source-grounded | In progress | 7.QUAN_LY_DU_AN/; 6.TAI_LIEU/6.1.bao_cao/ | final-repository-hotfix branch | Retrospective reconstruction is explicitly labeled.